## Version Control
Version # | Implemented | Revision | Approved | Approval | Reason
| By | Date | By | Date
1 | Najah Ismail | 2024-10-07 | Mishra Apurva | 2024-10-09 | Initial Risk Management Log Draft

## Risk Management Log
No. | Risk Type | Risk Description | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Inability to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delay the deployment date. | Mishra Apurva | Mitigate | Have regular meetings and updates from the developer team to check on their progress.
2 | Software | Feature creep | High | High |  | 9 | Will delay the project and may not be able to meet the set deadlines. | Gambhir Dhruv | Avoid | Maintain traceability between documentation and code to not go beyond the specified requirements.
3 | Communication | Miscommunications between team members | High | Medium |  | 7 | Overlapping of codes which may lead to errors while running the program, and documentation may be inaccurate. | Najah Ismail | Avoid | Ensure transparency between group members when it comes to updating of work done, which will lead to less miscommunication and conflicting information.
4 | Resource | Unavailability of project memebers | Medium | Medium |  | 6 | Staff's work will not be completed. | Mishra Apurva | Transfer | Transfer the workload to other staff workers in order to ensure that work is still completed by deadlines.
5 | Software | System not meeting requirements | Low | High |  | 5 | Scheduled releases may be affected as that would lead to more debugging and testing. | Nithya Hariharan | Avoid | Ensure that testing is done early so that the system can be checked against requirements with ample spare time.
6 | Communication | Misunderstanding/Miscommunication of requirements from stakeholders | Low | High |  | 6 | Requires us to redesign our application which delays the project | Mishra Apurva | Avoid | Establish a clear set of requirements and ensure that it is signed and agreed by both parties beforehand.
7 | External | Data breahces or security vulerability | Low | High |  | 6 | Loss in customer trust and brand reputation | Najah Ismail | Avoid | Encrypt personal information given to the application so that hackers will not be able to access it.
8 | Communication | Incomplete Documentation | Low | Low |  | 2 | May result in miscommunication between team members and may create issues in the future when maintaining the software | Nithya Hariharan | Avoid | Perform consistent review of existing documentation and create a list of documentation to be maintained. Ensure that version control is in place for each document so that it is easy to track changes and verify information.
9 | Software | Dependency on third-party services (Firebase, AWS) causing outages or failures | Low | High |  | 6 | The service will not be developed or made available for testing and production in time. | Mehta, Viral Sujal | Transfer | Ensure that the services are available. Any projected disruptions must be communicated before hand to account for in the development process.
10 | Software | Limited scalability under high traffic conditions | Low | Medium |  | 3 | The application will not meet stakeholder requiremtents and production quality will be substantial. | Tan Jing Jie | Solve | An investigation into the causes and a new architecture will be developed in discussion with the Tech Lead and relevent stake holders.
11 | Software | Minor Bugs | Low | low |  | 1 | code will nto be executed and will result in application crash. | Tan Shu Hua, Samantha | Solve | Any bugs must be solved and code changes tested before moving into production.
12 | Software | Inability to meet intermediate milestones of project development | High | Medium |  | 8 | The project development is delayed and there is increased tensions among the team. | Mishra Apurva | Avoid | Meetings are held regularly to receive status updates on the developemnt process.
13 | Software | Inconsistencies in code design | Medium | Medium |  | 6 | Code will be harder to read and understand and there is possibility for bugs. | Gambir Dhruv | Avoid | Adhere to proper programming style and principles e.g. names, alignment, locality, comments
14 | Software | Increased server load from higher user base or malicious attack | Medium | High |  | 8 | There is a risk of data breach and will be loss of trust in the product and development team. | Gambir Dhruv | Avoid | Adhere to best security practices. Any vulnerbilities in the code must be sought out and corrected.

## Top 10 Risks
No. | Risk Type | Risk | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Inability to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delay the deployment date. | Mishra Apurva | Mitigate | Have regular meetings and updates from the developer team to check on their progress.
2 | Software | Feature creep | High | High |  | 9 | Will delay the project and may not be able to meet the set deadlines. | Gambhir Dhruv | Avoid | Maintain traceability between documentation and code to not go beyond the specified requirements.
3 | Communication | Miscommunications between team members | High | Medium |  | 7 | Overlapping of codes which may lead to errors while running the program, and documentation may be inaccurate. | Najah Ismail | Avoid | Ensure transparency between group members when it comes to updating of work done, which will lead to less miscommunication and conflicting information.
4 | Resource | Unavailability of project memebers | Medium | Medium |  | 6 | Staff's work will not be completed. | Mishra Apurva | Transfer | Transfer the workload to other staff workers in order to ensure that work is still completed by deadlines.
5 | Software | System not meeting requirements | Low | High |  | 5 | Scheduled releases may be affected as that would lead to more debugging and testing. | Nithya Hariharan | Avoid | Ensure that testing is done early so that the system can be checked against requirements with ample spare time.
6 | Communication | Misunderstanding/Miscommunication of requirements from stakeholders | Low | High |  | 6 | Requires us to redesign our application which delays the project | Mishra Apurva | Avoid | Establish a clear set of requirements and ensure that it is signed and agreed by both parties beforehand.
7 | External | Data breahces or security vulerability | Low | High |  | 6 | Loss in customer trust and brand reputation | Najah Ismail | Avoid | Encrypt personal information given to the application so that hackers will not be able to access it.
12 | Software | Inability to meet intermediate milestones of project development | High | Medium |  | 8 | The project development is delayed and there is increased tensions among the team. | Mishra Apurva | Avoid | Meetings are held regularly to receive status updates on the developemnt process.
14 | Software | Increased server load from higher user base or malicious attack | Medium | High |  | 8 | There is a risk of data breach and will be loss of trust in the product and development team. | Gambir Dhruv | Avoid | Adhere to best security practices. Any vulnerbilities in the code must be sought out and corrected.
9 | Software | Dependency on third-party services (Firebase, AWS) causing outages or failures | Low | High |  | 6 | The service will not be developed or made available for testing and production in time. | Mehta, Viral Sujal | Transfer | Ensure that the services are available. Any projected disruptions must be communicated before hand to account for in the development process.

## Matrix
Impact | High | 1. Data breaches or security vulnerabilities 2. Dependency on third-party services (Firebase, AWS) causing outages or failures | 1. Insufficient user testing leading to usability issues | 1. Feature Creep
2. Inability to meet Project Deadline
3. Increased server load from higher user base or malicious attack
| Medium | 1. Unavailability of project members. 2. Incomplete Documentation 3. Limited scalability under high traffic conditions | 1. Inconsistencies in code design | 1. Miscommunications between team members
2. Inability to meet intermediate milestones of project development
| Low | 1. Minor bugs
Probability